COSTLENS

AI Procurement Intelligence Platform

STARTUP LAUNCH PLAYBOOK

From Part-Time Side Project to Full-Time Brand

A 4-Phase, 18-Month Roadmap

Prepared for: Pratap Sahoo, Founder

Date: March 2026

Version: 1.0

This playbook is designed for a procurement leader launching a SaaS startup while employed full-time. It accounts for Indian market dynamics, limited initial capital, and the founder's unique domain authority in manufacturing procurement.

# Executive Summary

CostLens has a rare advantage: it is being built by someone who IS the target customer. 25+ years of procurement experience, managing hundreds of crores in annual spend, negotiating with hundreds of Indian suppliers, and building the exact Excel templates that CostLens replaces. This is not a tech founder searching for a problem. This is a domain expert who has already solved the problem for himself and is now productizing the solution.

The playbook is structured in 4 phases over 18 months:

| Phase | Timeline | Mode | Goal | Key Milestone |
| --- | --- | --- | --- | --- |
| 1: Validate | Months 1-3 | Part-time | Prove demand | 50 users, 5 paying |
| 2: Traction | Months 4-8 | Part-time | Product-market fit | Rs 1L MRR, 30 paying |
| 3: Scale | Months 9-14 | Transition | Growth systems | Rs 5L MRR, 150 paying |
| 4: Brand | Months 15-18 | Full-time | Market leadership | Rs 15L+ MRR, thought leader |

Total estimated investment: Rs 5-8 Lakhs over 18 months. Expected break-even: Month 10-12. No external funding required until Phase 4 (if at all).

# Table of Contents

Phase 1: Validate (Months 1-3) — Part-Time

1.1 Legal Foundation

1.2 Domain, Hosting & Infrastructure

1.3 Soft Launch Strategy

1.4 Content-Led Acquisition

1.5 First 50 Users Playbook

1.6 Pricing Validation

1.7 Phase 1 Budget

Phase 2: Traction (Months 4-8) — Part-Time

2.1 Product Iteration from Feedback

2.2 Content Machine

2.3 Community Building

2.4 First Rs 1L MRR

2.5 Partnerships & Distribution

2.6 Phase 2 Budget

Phase 3: Scale (Months 9-14) — Transition

3.1 When to Quit Your Job

3.2 Team Building

3.3 Growth Channels

3.4 Enterprise Sales

3.5 Phase 3 Budget

Phase 4: Brand Leadership (Months 15-18) — Full-Time

4.1 Thought Leadership at Scale

4.2 Conferences & Events

4.3 Funding Decision

4.4 Long-Term Vision

Appendix A: Brand Identity Guidelines

Appendix B: Content Calendar Template

Appendix C: Unit Economics Model

Appendix D: Risk Mitigation Plan

# PHASE 1: VALIDATE (Months 1-3)

Mode: Part-time (evenings + weekends). Goal: 50 registered users, 5 paying. Budget: Rs 1.5L

## 1.1 Legal Foundation (Week 1-2)

Get this done first. It protects you and makes the business real.

Company Registration

- Register as Private Limited Company (not LLP, not proprietorship). Investors and enterprise clients expect Pvt Ltd.

- Name: CostLens Technologies Private Limited (check MCA availability first, have 3 backup names)

- Register on MCA portal via a CA. Cost: Rs 8,000-12,000 including GST registration

- Director: You (sole director initially). Add a co-director if needed for compliance

- Registered office: Your home address is fine initially

IP Protection

- File Trademark application for 'CostLens' (Class 9: software, Class 42: SaaS). Cost: Rs 4,500-9,000 per class via a trademark agent

- The TM symbol can be used immediately. Registered mark comes after registration (12-18 months)

- Domain trademark is separate from company name — do both

Employment Conflict Check

- Review your employment contract at HMC Group for non-compete, IP assignment, and moonlighting clauses

- Most Indian employment contracts have broad IP clauses — but they apply to work done during employment using company resources

- CostLens is your personal IP if: built on personal time, on personal devices, not using HMC data, not competing directly with HMC's business (HMC makes bicycles, not software)

- If in doubt, consult an employment lawyer (Rs 5,000-10,000 for a one-time opinion)

CRITICAL: Never use HMC data, HMC supplier information, or HMC equipment for CostLens. Keep a clear separation from Day 1.

Bank Account & Compliance

- Open current account in company name (HDFC/ICICI — good for startups)

- Register on Razorpay (for subscription payments) — needs company PAN, bank account, GST

- GST registration is mandatory if revenue > Rs 20L/year (apply early, needed for B2B invoicing)

## 1.2 Domain, Hosting & Infrastructure (Week 2-3)

| Item | Recommended | Cost/Year | Priority |
| --- | --- | --- | --- |
| Domain | costlens.in + costlens.com | Rs 2,000 | Day 1 |
| Email | Google Workspace (hello@costlens.in) | Rs 1,500/yr | Day 1 |
| Frontend Hosting | Vercel (free tier) or Cloudflare Pages | Rs 0 | Week 2 |
| Backend Hosting | Railway.app ($5/mo) or Render | Rs 5,000/yr | Week 2 |
| Database | Supabase free or Railway PostgreSQL | Rs 0-3,000/yr | Week 2 |
| File Storage | AWS S3 (pay-as-you-go) | Rs 500/yr initially | Week 2 |
| Anthropic API | Pay-as-you-go | Rs 3,000-8,000/mo | Week 3 |
| Analytics | PostHog (free tier) or Mixpanel | Rs 0 | Week 3 |
| Error Tracking | Sentry (free tier) | Rs 0 | Week 3 |

Total infrastructure cost: Rs 5,000-15,000/month depending on usage. The beauty of SaaS is that costs scale with users, and each user pays more than they cost.

Anthropic API Cost Economics

This is your biggest variable cost. Let's model it:

| Feature | Tokens/Call | Cost/Call (Rs) | Monthly at 100 calls |
| --- | --- | --- | --- |
| Price Check | ~3,000 | Rs 2-3 | Rs 250 |
| Contract Analyzer | ~8,000 | Rs 8-10 | Rs 900 |
| RFQ Comparator | ~8,000 | Rs 8-10 | Rs 900 |
| Negotiation Brief | ~5,000 | Rs 5-6 | Rs 550 |
| Report Analysis | ~8,000 | Rs 8-10 | Rs 900 |
| Smart Email | ~1,500 | Rs 1-2 | Rs 150 |

A Pro user at Rs 1,999/mo using 50 credits costs you roughly Rs 200-300 in API fees. That is 85%+ gross margin. Excellent SaaS economics.

## 1.3 Soft Launch Strategy (Week 3-4)

Do NOT do a grand launch. Do a quiet, controlled soft launch to a small group.

Step 1: Inner Circle (10 people)

- Personally message 10 procurement professionals you know and trust

- NOT from HMC — use your broader industry network (IIMM contacts, ex-colleagues, LinkedIn connections)

- Ask them to try the free tier and give honest feedback

- Offer them 3 months free Pro access as founding beta users

Step 2: LinkedIn Soft Launch (Week 4)

Post a personal story on LinkedIn. Not a product launch. A story.

Example post: 'After 25 years in procurement, I have built the same Excel should-cost template at 4 different companies. Every time, starting from scratch. Last year, I started building the tool I wish I had on Day 1 of my career. Today, I am quietly sharing it with a few fellow procurement professionals. If you manage Rs 50 Cr+ in spend and negotiate with Indian suppliers daily, I would love your feedback. DM me for early access. It is free.'

This type of post will outperform any product announcement because:

- It is a personal narrative, not an ad

- It is from a peer (GCPO), not a startup founder

- It creates scarcity ('quietly sharing', 'DM me')

- It qualifies the audience naturally (Rs 50 Cr+ spend)

Step 3: Ebook Lead Magnet (Week 4)

- Upload your 3 published ebooks to CostLens

- Gate them behind free registration (email required)

- Share on LinkedIn: 'Free ebook: 100-Day Cost Reduction Program — the exact playbook I used to deliver Rs 40 Cr savings'

- Every ebook download = a registered user who sees the full platform

## 1.4 Content-Led Acquisition (Ongoing)

Content is your unfair advantage. You have 25 years of stories, frameworks, and battle scars. No marketing agency can replicate this. Content is how you build a brand without spending money.

LinkedIn Strategy (3 posts/week)

You need to become the 'procurement voice' on LinkedIn. Here is the formula:

| Day | Post Type | Example | Goal |
| --- | --- | --- | --- |
| Monday | War Story | 'A supplier quoted Rs 480/pc for a part that should cost Rs 340. Here is how I caught it...' | Authority |
| Wednesday | Framework | 'My 5-step vendor negotiation checklist (used it 200+ times)' — share as carousel | Lead gen |
| Friday | Hot Take | '90% of procurement teams don't know their true landed cost. Here is why...' | Engagement |

Content Rules

- Always write from first person — 'I negotiated', 'I discovered', 'In my 25 years'

- Use Rs figures, not vague claims — 'Rs 3.2 Cr savings' not 'significant savings'

- Name processes, not products — 'zero-based costing' not 'CostLens features'

- End every post with a question or challenge to the audience

- Mention CostLens only in comments, never in the main post (first 3 months)

- Use Indian manufacturing examples — Rajkot, Ludhiana, Pune, Coimbatore

- Post between 8:00-9:00 AM IST (peak LinkedIn for Indian professionals)

YouTube Strategy (1 video/week, starting Month 2)

Short (5-8 min) screen-share tutorials:

- 'How to build a should-cost model in 5 minutes' (screen recording of CostLens)

- 'Is your supplier overcharging? This AI tool checks in 30 seconds'

- 'I analyzed a 38-page supplier contract with AI. Here is what it found.'

YouTube is underrated for B2B SaaS in India. Procurement managers DO watch YouTube for learning. And unlike LinkedIn, YouTube content has a long shelf life — a good video gets views for years.

## 1.5 First 50 Users Playbook

Your first 50 users will NOT come from ads, SEO, or viral content. They will come from personal outreach and word-of-mouth.

| Channel | Target | Expected Users | Cost |
| --- | --- | --- | --- |
| Personal LinkedIn network | Direct DMs to procurement contacts | 15-20 | Rs 0 |
| LinkedIn posts (organic) | Free sign-ups from content engagement | 10-15 | Rs 0 |
| Ebook downloads | Gated content leads to registration | 10-15 | Rs 0 |
| IIMM / procurement community | WhatsApp groups, forums | 5-10 | Rs 0 |
| Referral from early users | 'Tell a colleague' | 5-10 | Rs 0 |

Personal Outreach Script (LinkedIn DM)

'Hi [Name], I see you are leading procurement at [Company]. I have been building a tool that does zero-based cost analysis — the kind we all wish we had but end up building in Excel every time. I would love 15 minutes of your feedback. Happy to give you free access. Would next [day] work for a quick call?'

Conversion Funnel (Month 1-3)

| Stage | Count | Conversion | Notes |
| --- | --- | --- | --- |
| Registered | 50 | 100% | Free sign-up |
| Tried a module | 35 | 70% | Activation metric |
| Used 5+ times | 20 | 40% | Retention signal |
| Hit upgrade prompt | 15 | 30% | Tried AI tool, hit credit wall |
| Paid (Pro) | 5 | 10% | Rs 1,999/mo each = Rs 10K MRR |

## 1.6 Pricing Validation

Your current pricing is reasonable but needs market testing:

| Plan | Price | Validation Signal | Adjust If... |
| --- | --- | --- | --- |
| Starter (Free) | Rs 0 | Registration rate | <5 signups/week = landing page problem |
| Professional | Rs 1,999/mo | Conversion to paid | <5% conversion = too expensive |
| Team | Rs 4,999/mo | Team adoption | No interest = drop for now |
| Enterprise | Custom | Inbound inquiries | Interest = real signal |

Pricing Psychology Tips

- Anchor against alternatives: 'A single should-cost from a consultant costs Rs 50K-2L. CostLens Pro gives you unlimited for Rs 1,999/mo'

- Anchor against current waste: 'If you overpay even 5% on Rs 50 Cr spend, that is Rs 2.5 Cr/year. CostLens costs Rs 24K/year.'

- Offer annual plan early (Rs 19,999/yr = Rs 1,667/mo). Reduces churn, improves cash flow

- Consider a Rs 999/mo 'Lite' plan if Rs 1,999 faces resistance (10 credits/mo, limited reports)

## 1.7 Phase 1 Budget

| Item | One-Time | Monthly | 3-Month Total |
| --- | --- | --- | --- |
| Company Registration + GST | Rs 12,000 | — | Rs 12,000 |
| Trademark (2 classes) | Rs 12,000 | — | Rs 12,000 |
| Domain + Google Workspace | Rs 3,000 | — | Rs 3,000 |
| Developer (backend integration) | Rs 50,000 | — | Rs 50,000 |
| Hosting + Infrastructure | — | Rs 5,000 | Rs 15,000 |
| Anthropic API | — | Rs 5,000 | Rs 15,000 |
| LinkedIn Premium (outreach) | — | Rs 2,500 | Rs 7,500 |
| Miscellaneous | — | Rs 3,000 | Rs 9,000 |
| TOTAL | Rs 77,000 | Rs 15,500 | Rs 1,23,500 |

Phase 1 investment: ~Rs 1.25 Lakhs. Recoverable with just 3 annual Pro subscribers (Rs 60K). Very low risk.

# PHASE 2: TRACTION (Months 4-8)

Mode: Part-time (evenings + weekends, more structured). Goal: Rs 1L MRR, 30 paying users. Budget: Rs 2L additional

## 2.1 Product Iteration from Feedback

By Month 4, you will have 50+ users and real feedback. Common patterns to expect:

| Feedback Theme | Likely Action | Priority |
| --- | --- | --- |
| 'I want to save my analyses' | Backend already handles this | Must-have (dev) |
| 'Can I export to PDF?' | Implement PDF generation | Must-have |
| 'My data columns don't match' | DataMapper already built, refine | Iterate |
| 'Need more Indian material rates' | Build rate database | High-value differentiator |
| 'Can my team use it?' | Team plan + shared workspace | Month 6+ |
| 'Can it integrate with SAP?' | Too early — note for Enterprise | Backlog |

Feature Prioritization: ICE Scoring

- Impact: How much revenue/retention will this drive? (1-10)

- Confidence: How sure are you this will work? (1-10)

- Ease: How easy is it to build? (1-10, where 10 = easy)

Score = I x C x E. Do the highest-scoring items first. Never build features that one user asked for — wait for patterns.

## 2.2 Content Machine

By Phase 2, content becomes systematic. You are no longer experimenting — you are building a machine.

Weekly Content Calendar

| Day | Platform | Content Type | Time |
| --- | --- | --- | --- |
| Monday | LinkedIn | Personal procurement story | 30 min |
| Tuesday | YouTube | Tutorial: CostLens walkthrough | 2 hrs |
| Wednesday | LinkedIn | Framework / template / carousel | 45 min |
| Thursday | Newsletter | Weekly procurement insight + tip | 1 hr |
| Friday | LinkedIn | Industry opinion / hot take | 30 min |
| Saturday | Blog | Long-form SEO article | 2 hrs |

Newsletter: 'The Procurement Edge'

Start an email newsletter from Month 4. This is your most valuable owned channel.

- Platform: Substack (free) or ConvertKit (Rs 800/mo)

- Frequency: Weekly (every Thursday)

- Content: 1 procurement insight + 1 CostLens feature tip + 1 industry data point

- Growth: Every CostLens registered user auto-subscribed (with opt-out)

- Target: 500 subscribers by Month 6, 2,000 by Month 12

SEO Strategy (Long Game)

Start creating blog content optimized for procurement searches:

- 'Should cost analysis template Excel free download' — give template, pitch CostLens

- 'How to negotiate with suppliers in India' — position as expert

- 'Procurement KPIs for manufacturing' — drives CPO audience

- 'Zero based costing example manufacturing' — exact CostLens use case

- 'Supplier cost breakdown sheet format' — CBS template download

Each blog post takes 2 hours but generates traffic for years. Target: 20 posts by Month 8.

## 2.3 Community Building

Build a community of procurement professionals around CostLens, not just a user base.

WhatsApp Community

- Create 'Procurement Excellence Circle' WhatsApp community (not group — community allows channels)

- Channels: General, Cost Engineering, Negotiations, Career, CostLens Updates

- Share a valuable insight daily (not CostLens marketing — genuine value)

- Target: 200 members by Month 8

Monthly Webinar: 'Procurement Power Hour'

- Free monthly Zoom webinar on procurement topics

- Topics: 'How to Run a Zero-Based Costing Program', 'Negotiation Masterclass', 'Steel Supply Chain Economics 2026'

- 30 min presentation + 30 min live Q&A

- Record and publish on YouTube (content repurposing)

- Registration drives CostLens sign-ups

- Feature a live CostLens demo in every webinar naturally

User Testimonials (Month 6+)

- Ask your 5 paying users for a 2-line quote

- Record 2-3 minute video testimonials (phone is fine)

- Ask: 'How much time does CostLens save you per week?' and 'What was your ROI in the first month?'

- Use real names, real companies, real Rs figures

## 2.4 Path to Rs 1L MRR

Rs 1L MRR (Rs 1,00,000/month) is your first real milestone. Here is the math:

| Scenario | Users | Revenue/User | MRR |
| --- | --- | --- | --- |
| 50 Pro Monthly | 50 | Rs 1,999 | Rs 99,950 |
| 30 Pro + 5 Team | 30+5 | Rs 1,999 + Rs 4,999 | Rs 84,965 |
| 20 Annual + 15 Monthly | 20+15 | Rs 1,667 + Rs 1,999 | Rs 63,325 |

Realistically, you need 40-50 paying users to hit Rs 1L MRR. At 10% free-to-paid conversion, that means 400-500 registered users. Achievable by Month 8 with consistent content + organic growth.

Churn Prevention (Critical)

- Weekly email showing value delivered: 'You ran 8 analyses this month, saving estimated Rs X'

- Feature reminder emails when a user has not logged in for 7 days

- Personal outreach to every churned user: 'What made you cancel?'

- Annual plans reduce churn dramatically (locked in for 12 months)

## 2.5 Partnerships & Distribution

IIMM (Indian Institute of Materials Management)

- Offer CostLens as an educational tool in IIMM training programs

- Conduct IIMM chapter workshops (free, 2-hour sessions)

- Positions CostLens as the 'official tool' for procurement education

CA / Cost Accountant Partnerships

- Cost accountants frequently do should-cost analysis for manufacturing clients

- Offer them a referral partnership: 20% recurring commission

- They become channel partners without CostLens spending on sales

ERP Consultants

- SAP/Oracle implementation consultants touch every manufacturing company

- CostLens is complementary (analyzes ERP data, does not compete with ERP)

- Partner for co-marketing: 'Upload your SAP data, get instant procurement insights'

## 2.6 Phase 2 Budget

| Item | Monthly | 5-Month Total |
| --- | --- | --- |
| Developer (part-time, features) | Rs 15,000 | Rs 75,000 |
| Hosting + Infrastructure | Rs 8,000 | Rs 40,000 |
| Anthropic API (growing) | Rs 10,000 | Rs 50,000 |
| Newsletter platform | Rs 800 | Rs 4,000 |
| Webinar tools (Zoom Pro) | Rs 1,500 | Rs 7,500 |
| Canva Pro (design) | Rs 500 | Rs 2,500 |
| Miscellaneous | Rs 5,000 | Rs 25,000 |
| TOTAL | Rs 40,800 | Rs 2,04,000 |

Phase 2 investment: ~Rs 2L. By Month 8, if you hit Rs 1L MRR, the business is self-sustaining.

# PHASE 3: SCALE (Months 9-14)

Mode: Transition from part-time to full-time. Goal: Rs 5L MRR, 150 paying users. Budget: Self-funded from revenue.

## 3.1 When to Quit Your Job

This is the biggest personal decision. Use these criteria (ALL must be true):

- CostLens MRR >= Rs 1.5L for 3 consecutive months (not a fluke)

- MRR is growing 15%+ month-over-month (trajectory matters)

- You have 6 months of personal expenses saved (Rs 6-10L runway)

- You have a clear path to Rs 5L MRR (pipeline, not hope)

- The business NEEDS you full-time (you are the bottleneck)

- Your family is aligned and supportive

Do NOT quit at the first sign of traction. Part-time founders who wait until the signal is undeniable have a much higher success rate than those who jump early on excitement.

Transition Plan (2 months)

- Month -2: Inform your employer, offer a 60-day transition (professional exit)

- Month -1: Hire or formalize a part-time developer and a content/VA person

- Month 0: Full-time on CostLens. First week: re-architect your time

Full-Time Time Allocation

| Activity | Hours/Week | Notes |
| --- | --- | --- |
| Product development | 10 | Feature specs, testing, UX decisions |
| Content creation | 10 | LinkedIn, YouTube, blog — your #1 growth engine |
| Sales calls / demos | 10 | Talk to users every single day |
| Operations | 5 | Billing, support, admin — automate aggressively |
| Strategy / partnerships | 5 | Build distribution and network |

## 3.2 Team Building

Keep the team tiny. A 3-person team can reach Rs 50L ARR in B2B SaaS.

| Role | When | Type | Monthly Cost | Where to Find |
| --- | --- | --- | --- | --- |
| Full-stack Developer | Month 9 | Full-time/contract | Rs 50-80K | Toptal, LinkedIn, Instahyre |
| Content + Social | Month 10 | Part-time/freelance | Rs 20-30K | LinkedIn, journalism grads |
| Customer Success | Month 12 | Part-time initially | Rs 20-30K | Ex-procurement juniors |

Who NOT to Hire Yet

- Sales team — you are the best salesperson (domain authority). Hire after Rs 10L MRR

- Marketing agency — they will not understand procurement. Keep content in-house

- CTO — not needed until 500+ users and complex infrastructure

- Co-founder — only if someone brings skills you fundamentally lack

## 3.3 Growth Channels

Channel 1: LinkedIn Outbound (Scalable)

- Use LinkedIn Sales Navigator (Rs 5,000/mo) to identify CPOs, Procurement Heads at manufacturing companies

- Send connection + value message: share a relevant ebook, not a sales pitch

- Funnel: Connection > Content engagement > Free trial > Pro conversion

- Target: 50 new connections/week, 5-10 conversions/month

Channel 2: Google Ads (Pay-per-click)

- Start small: Rs 15,000/mo budget

- Target high-intent keywords: 'should cost analysis tool', 'procurement cost analysis software India'

- Landing page: Direct to free registration (not pricing page)

- Expected CPA: Rs 500-1,500 per registered user, Rs 5,000-15,000 per paying user

- Scale only if CAC:LTV ratio is 1:3 or better

Channel 3: Industry Events / Workshops

- Conduct free workshops at industry clusters: Ludhiana, Rajkot, Pune, Coimbatore, Bangalore

- 'Zero-Based Costing Masterclass' — 3-hour workshop, 30-50 attendees

- Every attendee = qualified lead (procurement professional at manufacturing company)

- Cost: Rs 10-15K per event (venue + travel). Expected: 5-10 conversions per event

Channel 4: Referral Program

- Launch: 'Refer a colleague, both get 10 free credits'

- Add in-app 'Share CostLens' button with unique referral link

- Track referral source for every new registration

## 3.4 Enterprise Sales Motion

Enterprise deals (Rs 5-15L/year) will come naturally by Month 10-12. Be ready:

Enterprise Needs (vs. Pro users)

- SSO integration (Azure AD, Google Workspace)

- Role-based access control (RBAC) for teams

- Data residency assurance (India-hosted)

- Custom SLA with support hours

- Invoice-based payment (not credit card)

- Integration with their ERP (usually SAP/Oracle)

Enterprise Pricing Strategy

Do not list enterprise pricing. Always say 'Custom pricing based on usage and team size.' This allows you to:

- Price based on their spend (1,000 Cr company can pay more than 100 Cr company)

- Include implementation support in the deal

- Offer multi-year contracts (12-24 months) for better cash flow

- Typical enterprise deal: Rs 8-15L/year for 5-20 users

## 3.5 Phase 3 Budget

By Phase 3, the business should be self-funding from revenue.

| Item | Monthly | Notes |
| --- | --- | --- |
| Your salary (founder) | Rs 1-1.5L | Pay yourself! Sustainable, not extravagant |
| Developer (full-time) | Rs 60-80K | Core product development |
| Content manager | Rs 20-30K | LinkedIn, blog, newsletter |
| Infrastructure + API | Rs 15-25K | Scales with users |
| Google Ads | Rs 15-20K | Paid acquisition test |
| LinkedIn Premium + tools | Rs 5K | Sales Navigator |
| Events + travel | Rs 10K | 1-2 workshops/month |
| TOTAL | Rs 2.5-4L/mo | Covered by Rs 5L+ MRR target |

# PHASE 4: BRAND LEADERSHIP (Months 15-18)

Mode: Full-time. Goal: Rs 15L+ MRR, recognized thought leader in Indian procurement.

## 4.1 Thought Leadership at Scale

By this stage, you are not just selling software. You are becoming the voice of modern procurement in India.

Brand Positioning Statement

CostLens is the AI-powered procurement intelligence platform built by Indian procurement professionals, for Indian procurement professionals. We help manufacturing companies negotiate from data, not guesswork.

Authority Building

- Publish 'State of Indian Manufacturing Procurement' annual report (using anonymized CostLens data)

- Get quoted in trade media (ET Manufacturing, CNBC-TV18 SME, BW Industrialist)

- Guest lecture at IIMs/IITs in supply chain management programs

- Write op-eds for procurement trade journals

- Launch 'CostLens Procurement Index' — monthly data on Indian manufacturing costs

Podcast: 'The Procurement Edge'

- Weekly 30-min podcast interviewing CPOs, supply chain leaders, cost engineers

- Host on Spotify, Apple Podcasts, YouTube

- Every episode features CostLens naturally

- This becomes a network-building machine (every guest = potential customer/partner)

## 4.2 Conferences & Events

CostLens Annual Summit: 'Procurement Excellence India'

By Month 18, host your own annual event:

- 200-300 attendees (procurement leaders from Indian manufacturing)

- Keynotes from industry CPOs and supply chain leaders

- CostLens product showcase + customer success stories

- Sponsorship from ERP vendors, material suppliers, logistics companies

- Revenue: Rs 5K ticket x 200 = Rs 10L (event should break even or profit)

Speaking at Industry Events

- CII Manufacturing Summit

- IIMM National Conference

- NASSCOM (for SaaS/tech positioning)

- ACMA / SIAM (automotive supply chain)

Every speaking slot = brand visibility to 200-500 qualified buyers.

## 4.3 The Funding Decision

By Month 15-18, you will face the funding question. Here is the framework:

When to NOT Raise Funding

- If you are growing 10-15%/month and profitable — you do not need it

- If you can reach Rs 1 Cr ARR without funding — you have massive leverage

- Bootstrapped SaaS companies retain 100% ownership and move faster

- Many Indian B2B SaaS companies (Zoho, Freshworks era) prove this works

When to Raise Funding

- If the market is winner-take-all and speed matters (competitor emerging)

- If you need enterprise features (SSO, ERP integration) requiring 10+ developers

- If you want to expand geographically (Southeast Asia, Middle East)

If You Raise

- Target: Rs 1-3 Cr seed round

- Investors: Blume Ventures, India Quotient, 100X.VC, LetsVenture angel syndicates

- Your pitch: 'I am the customer. I built the product. It has Rs X MRR growing Y%/month. Indian manufacturing procurement is Rs 50 Lakh Crore market. We are the only AI-native platform built for Indian supply chains.'

- The fact that you are a sitting/ex-GCPO building procurement software is a VERY strong founder-market fit story

## 4.4 Long-Term Vision (Year 2-5)

Product Expansion Roadmap

| Year | Feature | Revenue Impact |
| --- | --- | --- |
| Year 2 | Indian Material Rate Database | Rs 500/mo subscription — pure recurring |
| Year 2 | ERP Integration (SAP, Oracle) | Unlocks enterprise deals |
| Year 3 | Procurement Marketplace | Platform revenue (transaction %) |
| Year 3 | Training & Certification Program | Rs 15K per certification |
| Year 4 | International Expansion (MENA, SEA) | 10x addressable market |
| Year 5 | Procurement AI Assistant (conversational) | Next-gen product |

Revenue Projections (Conservative)

| Month | MRR | ARR | Paying Users | Team Size |
| --- | --- | --- | --- | --- |
| Month 3 | Rs 10K | Rs 1.2L | 5 | 1 (you) |
| Month 8 | Rs 1L | Rs 12L | 50 | 1.5 |
| Month 12 | Rs 3L | Rs 36L | 120 | 3 |
| Month 18 | Rs 8L | Rs 96L | 300 | 5 |
| Month 24 | Rs 20L | Rs 2.4 Cr | 600 | 8 |
| Month 36 | Rs 50L | Rs 6 Cr | 1,500 | 15 |

# Appendix A: Brand Identity Guidelines

Brand Name & Tagline

Primary: CostLens

Tagline: See the real cost. Negotiate from data.

Long form: AI-powered procurement intelligence for Indian manufacturing

Brand Voice

| Attribute | We Are | We Are NOT |
| --- | --- | --- |
| Expertise | The veteran who has done it 1000 times | The tech startup that just learned procurement |
| Tone | Direct, practical, Rs-focused | Jargon-heavy, consultant-speak, fluffy |
| Language | 'Here is how to save Rs 3.2 Cr' | 'Leverage synergies for procurement outcomes' |
| Personality | Sharp colleague who shares templates | Sales rep who cold-emails you |
| Values | Data over opinion. Transparency. | Hype, false urgency, misleading claims |

Visual Identity

Primary Color: #1B4F72 (deep navy) — trust, expertise, authority

Accent Color: #2E86C1 (bright blue) — technology, intelligence

Success Color: #10B981 (green) — savings, positive results

Warning Color: #F59E0B (amber) — alerts, attention

Error/Risk Color: #EF4444 (red) — overpricing, risk

Font (Headings): Bricolage Grotesque — modern, distinctive

Font (Body): DM Sans — clean, readable

Font (Numbers): IBM Plex Mono — data, calculations

Logo Concept

The CostLens logo should communicate: precision + insight + Indian manufacturing. Concept: A magnifying lens overlaid on a cost breakdown bar chart, with the lens revealing internal components.

Commission from: 99designs (Rs 25K for logo contest) or Dribbble freelancer (Rs 15-30K)

Domain & Social Handles

| Platform | Handle | Priority |
| --- | --- | --- |
| Website | costlens.in / costlens.com | Register both, Day 1 |
| LinkedIn Company | linkedin.com/company/costlens | Create immediately |
| YouTube | youtube.com/@costlens | Create immediately |
| Twitter/X | @costlens_in | Register (low priority) |
| Instagram | @costlens.in | Register (not primary) |

# Appendix B: Content Calendar Template (Month 1)

| Week | Mon (LinkedIn) | Wed (LinkedIn) | Fri (LinkedIn) | Sat (Blog) |
| --- | --- | --- | --- | --- |
| Week 1 | War story: negotiation saved Rs 40L | Framework: 5-step should-cost checklist | Hot take: Why Excel is killing procurement | Should-Cost Analysis Guide |
| Week 2 | Data: steel price trends Q1 | Template: vendor scorecard (image) | Question: Biggest procurement pain? | How to Read a CBS |
| Week 3 | Case: caught a 30% overcharge | Framework: make vs buy tree | AI will replace 60% of procurement tasks | Price Variance Analysis Guide |
| Week 4 | Personal: lessons from 25 years | Template: negotiation prep checklist | Industry observation + ebook CTA | Procurement KPIs Guide |

# Appendix C: Unit Economics Model

| Metric | Value | Notes |
| --- | --- | --- |
| Monthly subscription (Pro) | Rs 1,999 | Primary revenue |
| Annual subscription (Pro) | Rs 19,999 | Rs 1,667/mo effective |
| Avg Revenue Per User | Rs 1,800/mo | Blended monthly + annual |
| Customer Acquisition Cost | Rs 5,000-15,000 | Organic-heavy keeps this low |
| Gross Margin | 85-90% | API cost is 10-15% of revenue |
| API cost per user | Rs 200-300/mo | 50 credits average usage |
| Infrastructure cost per user | Rs 50-100/mo | Hosting, storage, compute |
| Customer Lifetime Value | Rs 36,000-54,000 | 18-30 month avg lifetime |
| LTV:CAC Ratio | 3:1 to 10:1 | Excellent (3:1 minimum for SaaS) |
| Monthly churn target | <5% | Industry avg 5-7% for SMB SaaS |
| Break-even users | 25-30 | At Rs 1,999/mo with minimal team |

The unit economics are very favorable. Organic content-led acquisition keeps CAC low. High gross margins (85%+) mean most revenue flows to the bottom line. This is a capital-efficient business.

# Appendix D: Risk Mitigation Plan

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Employer discovers and objects | Low | High | Keep complete separation. No HMC data, devices, or time |
| Anthropic API pricing increases | Medium | Medium | Build abstraction layer; can switch to alternatives |
| Competitor launches similar tool | Medium | Medium | Your domain authority is the moat. 25 years cannot be copied |
| Low conversion to paid | Medium | High | Test pricing (Rs 999 tier), add more free value |
| Churn exceeds 8%/month | Medium | High | Personal outreach to every churning user |
| Developer leaves | Medium | Medium | Document everything, have backup freelancers |
| AI generates incorrect analysis | High | Medium | 'AI-generated, verify' disclaimers. Build feedback loops |
| Slow user growth | Medium | High | Double down on content. Content compounds over 6-12 months |

--- END OF PLAYBOOK ---

Built with conviction. Launched with discipline. Scaled with content.